## ProjectTeam
Name | GitHub Alias | Shorthand | Role
Amalathas, Kevin | amalathask | ka | Developer
Biasutti, Yannis | biasutti | yb | Developer
Joder, Markus | jodem1 | mj | Developer
Moeri, Alexandre Reinhard | moera1 | am | Scrum Master
Rindlisbacher, José Miguel | Iniwuijshi | jr | Developer
Künzler, Urs | UrsKuenzler | ku | Product Owner
Vogel, Jürgen | vgj1 | vj | Product Owner

## Available Ressources
Sprint | Per Team Member (h) | Total (h) | Date From | Date To
1 | 8 | 40 | 2020-05-04 | 2020-05-12
2 | 14 | 70 | 2020-05-12 | 2020-05-26
3 | 6 | 30 | 2020-05-26 | 2020-06-08

## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original (h) | Effort Plan Updated (h) | Effort Actual (h) | Status
1 | Login to Application Dashboard | A health visitor logs in to the application to see the application dashboard. | high | 16 | 16 | 5 | waiting
2 | View Patients | A health visitor wants to see all of his patients and see their profiles | high | 12 | 11 | 0 | waiting
3 | View Calendar | A health visitor checks his upcoming appointments and is able to navigate to the patient | high | 12 | 11 | 0 | waiting
4 | Create Visit Protocol | A health visitor creates a protocol of a visit | high | 16 | 0 | 0 | waiting
5 | View Protocol History | A health visitor checks a patients previous protocols | high | 8 | 0 | 0 | waiting
6 | Search Protocol History | A health visitor searches for a specific protocol | medium | 16 | 0 | 0 | waiting
7 | Receive Notifications | A health visitor receives a notification when another health visitor creates a protocol related to one of his patients | medium | 16 | 0 | 0 | waiting
8 | Edit Protocol | A health visitor wants to edit an already existing protocol | low | 12 | 0 | 0 | waiting
9 | Call or Other Protocol | A health visitor creates a protocol that is not linked to a visit | low | 12 | 0 | 0 | waiting
10 | Check FAQ | A health visitor has a question during one of his visits an checks the FAQ | medium | 12 | 0 | 0 | waiting
11 | Appointment Changes | The health visitor receives Notifications for changed appointment | very low | 8 | 0 | 0 | waiting

## Sprint Backlog
ID | Product ID | Sprint | Name | Description | Components | Owner | Reviewer | Priority | Effort Plan Original (h) | Effort Plan Updated (h) | Effort Actual (h) | Status
1.1 | 1 | 1 | HealthVisitor Model | Model for Health Visitor | HealthVisitor: Model | jr | yb | high | 1 | 1 |  | work in progress
1.2 | 1 | 1 | Create HealthVisitor Test Set | Create a Test Set of at least 3 Health Visitors with all relevant attributes and ressources (including profile picture) | HealthVisitor: Test Data | jr | yb | medium | 1 | 1 | 1 | done
1.3 | 1 | 1 | Mock HealthVisitor API | Create API endpoint api/healthvisitors that returns all health visitors on GET | HealthVisitor: Mock API | yb | jr | medium | 2 | 2 | 3 | done
1.4 | 1 | 1 | Create Accounts Test Set | Create a Test Set of Login Credentials for all Health Visitor in the corresponding Test Set. Should contain login name and password as well as a reference to the Health Visitor data point | Accounts: Test Data | jr | yb | medium | 1 | 1 | 1 | done
1.5 | 1 | 1 | Mock Authentication API | Create API endpoint api/login that validates login credentials | Mock API | yb | jr | medium | 1 | 1 |  | work in progress
1.6 | 1 | 1 | Login View | Create a Login View that allows a user to Login with username and password, show a wrong password indication when appropriate, forward sucessful login to the dashboard | Login: View, Presenter | mj | am | high | 2 | 2 |  | work in progress
1.7 | 1 | 1 | Navigation Architecture | Set up page skeletons and a routing mechanism | UI | mj | am | high | 2 | 2 |  | waiting
1.8 | 1 | 1 | Navigation Component | Create a Navigation Subcomponent that provides Navigation to Appointments, Protocols, Patients and FAQ. The Navigation should reflect in which section the user currently is. | UI | mj | am | medium | 2 | 2 |  | waiting
1.9 | 1 | 1 | Dashboard View | Create a Dashboard View which displays to logged in Health visitors name and profile picture as well as space for notifications and upcoming appointments. Furthermore it contains the Navigation Component | Dashboard: View, Presenter | mj | am | high | 2 | 2 |  | waiting
2.1 | 2 | 1 | Patient Model | Model for Patient | Patient: Model | jr | yb | high | 1 | 1 |  | waiting
2.2 | 2 | 1 | Create Patient Test Set | Create a Test Set of at least 6 Patients with all relevant attributes and ressources (including profile picture) | Patient: Test Data | jr | yb | medium | 1 | 1 |  | waiting
2.3 | 2 | 1 | Mock Patient API | Create API endpoint api/patients that returns all health visitors on GET | Patient: Mock API | yb | jr | medium | 1 | 1 |  | waiting
2.4 | 2 | 1 | PatientList View | Create a View that displays all Patients, consider wether there exists a relationship to the health visitor and either prioritize accordingliy or hide non relevant ones. This should also display the general navigation bar. | Patient: View, Presenter | am | ka | high | 2 | 2 |  | work in progress
2.5 | 2 | 1 | PatientProfile View | Create a View that displays a single patients details, space for his/her upcoming appointments, space for his/her protocols. Includes a back button and a button to create a new protocol. | Patient: View, Presenter | am | ka | medium | 4 | 4 |  | waiting
3.1 | 3 | 1 | Appointment Model | Model for Appointment | Appointment: Model | jr | yb | high | 2 | 2 |  | waiting
3.2 | 3 | 1 | Create Appointment Test Set | Create a Test Set of at least 20 Appointments that cover different relationships | Appointment: Test Data | jr | yb | medium | 2 | 2 |  | waiting
3.3 | 3 | 1 | Mock Appointment API | Create API endpoint api/appointments that returns all Appointments on GET | Appointment: Mock API | yb | jr | medium | 1 | 1 |  | waiting
3.4 | 3 | 1 | AppointmentList View | Create a View that displays all future appointments of a HealthVisitor. This should also display the general navigation bar. | Appointment: View, Presenter | ka | mj | medium | 4 | 4 |  | work in progress
3.5 | 3 | 1 | AppointmentDetails View | Create a View that displays the Details of an appointment. Includes a back button and a button to create a new protocol. | Appointment: View, Presenter | ka | mj | medium | 2 | 2 |  | waiting
1.10 | 1 | 1 | Next appointments on Dashboard | Include a Healthvisitor next appointments on the dashboard, each item should lead to the corresponding detail view. A Link to see all Appointments should be provided. | Dashboard: View, Presenter; Appointment: Model | ka | mj | low | 2 | 2 |  | waiting
2.6 | 2 | 1 | Next appointments on Patient profile | Display the upcoming appointments of a patient on his profile. | Patient: View, Presenter; Appointment: Model | am | ka | low | 2 | 2 |  | waiting
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!
#VALUE!

## Review
Sprint 1 per Person |  |  | Planned Hours
Name | GitHub Alias | Shorthand | Available | Ownership | Review
Amalathas, Kevin | amalathask | ka | 8 | 8 | 8
Biasutti, Yannis | biasutti | yb | 8 | 5 | 9
Joder, Markus | jodem1 | mj | 8 | 8 | 8
Moeri, Alexandre Reinhard | moera1 | am | 8 | 8 | 8
Rindlisbacher, José Miguel | Iniwuijshi | jr | 8 | 9 | 5

## BurndownChart
Sprint | Time of Record | Remaining Effort | Remaining Ressources
1 | 2015-09-15 | 200 | 200
1 | 2015-09-16 | 190 | 180

## Status
waiting
work in progress
done
cancelled